## example
Task Name: (Dependencies top to bottom) | [8 empty] | David | Casey | Cuong | Kyle | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 2
|  | Design architecture | Project Manager | David, Casey | 12 |  | 2 |  | 2 | 0 |  |  | 2
| Requirements |  |  |  |  | 9 |  | 9 |  |  |  |  | 0
|  | Gather | Requirements Engineer | David, Casey | 2 |  | 3 |  | 2 | 1 |  |  | 3
|  | Analyze | Requirements Engineer | David, Casey | 4 |  | 3 |  | 2 | 1 |  |  | 3
|  | Specify | Requirements Engineer | David, Casey | 3 |  | 3 |  | 1 | 2 |  |  | 3
| Documentation |  |  |  |  | 28 |  | 38.5 |  |  |  |  | 0
|  | Project Charter | Project Manager | Casey, David | 2 |  | 3 |  | 0 | 3 |  |  | 3
|  | Release Plan | Project Manager | David, Casey | 2 |  | 3.5 |  | 0.5 | 3 |  |  | 3.5
|  | Requirements Document | Project Manager, Requirements Engineer | Casey, David | 5 |  | 6.5 |  | 0.5 | 6 |  |  | 6.5
|  | Project Plan | Project Manager, Developers | Casey, David, Kyle, Cuong | 5 |  | 8 |  | 0 | 6 |  | 2 | 8
|  | Architecture Document | Architect | David, Casey | 4 |  | 4 |  | 2 | 2 |  |  | 4
|  | Test Report | Tester | Casey, David | 8 |  | 7 |  | 1 | 6 |  |  | 7
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Casey, David, Kyle, Cuong | 2 |  | 6.5 |  | 0.5 | 5 |  | 1 | 6.5
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 61 |  | 78 |  |  |  |  | 0
|  | Determine technology needs | Developer | Kyle, Cuong | 1 |  | 2 |  |  |  | 1 | 1 | 2
|  | Research and learn new language and environment | Developer | Kyle, Cuong | 20 |  | 32 |  | 1 |  | 22 | 9 | 32
|  | Set up proxy server software | Developer | Kyle, Cuong | 8 |  | 5 |  | 5 |  |  |  | 5
|  | Write basic proxy code | Developer | Kyle, Cuong | 5 |  | 10 |  | 10 |  |  |  | 10
|  | Implement classes | Developer | Kyle, Cuong | 10 |  | 12 |  |  |  |  | 12 | 12
|  | Create HTTP handling code | Developer | Kyle, Cuong | 8 |  | 5 |  |  |  |  | 5 | 5
|  | Write code to store user name locally | Developer | Kyle, Cuong | 2 |  | 8 |  |  |  |  | 8 | 8
|  | Write code for managing HTTP session | Developer | Kyle, Cuong | 5 |  | 4 |  |  |  |  | 4 | 4
|  | Unit Testing | Developer | Kyle, Cuong | 2 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 6 |  | 5 |  |  |  |  | 0
|  | System Testing | Tester | Casey, David | 2 |  | 2 |  | 1 | 1 |  |  | 2
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 |  | 1 |  |  |  |  | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | David, Casey | 2 |  | 2 |  | 1 | 1 |  |  | 2
Iteration 2: | Design |  |  |  |  | 12 |  | 3.6 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | David, Casey | 2 |  | 0.5 |  | 0.5 |  |  |  | 0.5
|  | Risk analysis | Project Manager | Casey, David | 2 |  | 1 |  | 0.5 | 0.5 |  |  | 1
|  | Design XML format | Developer | Cuong, Kyle | 1 |  | 0.1 |  |  |  |  | 0.1 | 0.1
|  | Design Perl XML-handling code | Developer | Cuong, Kyle | 5 |  | 0 | [5 empty] | 0
|  | Create UI design for balance screen | Developer | Cuong, Kyle | 2 |  | 2 |  |  |  |  | 2 | 2
| Development |  |  |  |  | 22 |  | 30 |  |  |  |  | 0
|  | Review requirements | Developer | Cuong, Kyle | 1 |  | 1.5 |  |  |  | 0.5 | 1 | 1.5
|  | Create XML parsing code | Developer | Cuong, Kyle | 5 |  | 3.5 |  |  |  | 3.5 |  | 3.5
|  | Handle XML data structure for retrieving balance | Developer | Cuong, Kyle | 10 |  | 15 |  | 3 |  | 12 |  | 15
|  | Implement UI | Developer | Cuong, Kyle | 4 |  | 8 |  |  |  | 2 | 6 | 8
|  | Unit Testing | Developer | Cuong, Kyle | 2 |  | 2 |  |  |  | 2 |  | 2
| Analysis |  |  |  |  | 6 |  | 5.5 |  |  |  |  | 0
|  | System Testing | Tester | Casey, David | 2 |  | 1.5 |  | 0.5 | 1 |  |  | 1.5
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 |  | 3.5 |  | 0.5 |  | 2 | 1 | 3.5
|  | Evaluate needs for next iteration | Project Manager | David, Casey | 2 |  | 0.5 |  | 0.5 |  |  |  | 0.5
Iteration 3: | Design |  |  |  |  | 22 |  | 7.5 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | David, Casey | 2 |  | 0.5 |  | 0.5 |  |  |  | 0.5
|  | Risk analysis | Project Manager | Casey, David | 2 |  | 1 |  | 0.5 | 0.5 |  |  | 1
|  | Create UI design for vendor locations | Developer | Kyle, Cuong | 10 |  | 4 |  | 1 |  |  | 3 | 4
|  | Design data structure for RSS location list | Developer | Kyle, Cuong | 8 |  | 2 |  | 2 |  |  |  | 2
| Development |  |  |  |  | 29 |  | 5 |  |  |  |  | 0
|  | Review requirements | Developer | Kyle, Cuong | 1 |  | 0 | [5 empty] | 0
|  | Develop code for processing vendor locations | Developer | Cuong, Kyle | 10 |  | 3 |  |  |  |  | 3 | 3
|  | Implement vendor map display | Developer | Kyle, Cuong | 8 |  | 0 |  |  |  |  | N/A | 0
|  | Display vendor information | Developer | Kyle, Cuong | 8 |  | 2 |  |  |  |  | 2 | 2
|  | Unit Testing | Developer | Kyle, Cuong | 2 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 5 |  | 2.1 |  |  |  |  | 0
|  | Acceptance Testing | Tester, Project Manager | David, Casey | 3 |  | 1.5 |  | 1 | 0.5 |  |  | 1.5
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 |  | 0.6 |  | 0.5 |  |  | 0.1 | 0.6
Total |  |  |  |  | 212 | 212 | 186.2 | 186.2 | 40.5 | 39.5 | 45 | 61.2 | 186.2

## Sheet2
Task Name: (Dependencies top to bottom) | [8 empty] | Josiah | Blake | Jimmy | Jacob | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 10 |  | 7.5
|  | Design architecture | Project Manager | Jimmy | 10 |  | 7.5 |  |  |  | 7.5
| Requirements |  |  |  |  | 15 |  | 15
|  | Gather | Requirements Engineer | All | 5 |  | 5 |  | 5 | 5 | 5 | 5 | 20
|  | Analyze | Requirements Engineer | All | 5 |  | 5 |  | 5 | 5 | 5 | 5 | 20
|  | Specify | Requirements Engineer | All | 5 |  | 5 |  | 5 | 5 | 5 | 5 | 20
| Documentation |  |  |  |  | 8 |  | 10
|  | Project Charter | Project Manager | All | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 8
|  | UI design | UI engineer | Blake | 3 |  | 4 |  |  | 4
|  | Requirements Document | Project Manager, Requirements Engineer | Josiah, Blake | 3 |  | 4 |  | 4 | 4
Coding
Iteration 1: | Development |  |  |  |  | 17 |  | 27
|  | Determine technology needs | Developer | All | 10 |  | 15 |  | 15 | 15 | 15 | 15 | 60
|  | Research and learn new language and environment | Developer | All | 5 |  | 10 |  | 10 | 10 | 10 | 10 | 40
|  | Database Design | Developer | Josiah | 3 |  | 3 |  | 3
|  | Init Commit for Program structure | Developer | Jimmy | 2 |  | 2 |  |  |  | 2 |  | 2
| Analysis |  |  |  |  | 5 |  | 5
|  | System Testing | Tester
|  | Bug fix as required | Tester, Developer
|  | Evaluate needs for next iteration | Project Manager | All | 5 |  | 5 |  | 5 | 5 | 5 | 5 | 20
Iteration 2: | Development |  |  |  |  | 24 |  | 23.5
|  | Landing Page UI | UI Developer | Blake/Jimmy | 5 |  | 4.5 |  |  | 4.5 |  |  | 4.5
|  | Login/Account creation authentication | Developer | Jacob | 8 |  | 8 |  |  |  |  | 8 | 8
|  | Database Schema | Developer | Josiah | 5 |  | 5 |  | 5 |  |  |  | 5
|  | Integrate existing code into Angular Environment | Developer/Project Manager | Josiah/Jimmy/Blake | 6 |  | 5.5 |  | 5.5 | 5.5 | 5.5 |  | 16.5
| Analysis |  |  |  |  | 3 |  | 3
|  | Testing newly built systems | Tester | Jimmy | 3 |  | 3 |  |  |  | 3 |  | 3
Iteration 3: | Development |  |  |  |  | 17 | 15
|  | Merge file structure for backend/frontend | Developer/Project Manager | Josiah/Jimmy | 4 |  | 3 |  | 2 |  | 1 |  | 3
|  | Create components for transactions, accounts, etc. | Developer | Josiah/Jimmy | 6 |  | 5 |  | 2 |  | 3 |  | 5
|  | Connect Database to application | Developer | Blake | 4 |  | 4 |  |  | 4 |  |  | 4
|  | Render transactions into table from backend | Developer | Jimmy/Jacob | 3 |  | 3 |  |  |  | 3 |  | 3
| Documentation |  |  |  |  | 7 | 8
|  | Create documentation for API calls | Developer | Blake/Jacob | 4 |  | 5 |  |  | 2.5 |  | 2.5 | 5
|  | Create architecture document | Project Manager | Josiah/Jimmy | 3 |  | 3 |  | 1.5 |  | 1.5 |  | 3
Iteration 4: | Development
|  | Login/Registration Forms Creation | Developer | Blake | 4 |  | 5 |  |  | 5 |  |  | 5
|  | Merging Forms with Database | Developer | Jimmy/Jacob | 6 |  | 6.5 |  |  |  | 3.25 | 3.25 | 6.5
|  | Transactions Component Creation | Developer | Jimmy | 4 |  | 3 |  |  |  | 3
|  | Nav Bar redesign | Developer | Josiah | 3 |  | 3 | [5 empty] | 3
|  | Back end development | Developer | Jacob | 10 |  | 10 |  |  |  |  | 10 | 10
Analysis
|  | Quality Assurance/Testing New Systems | Tester/Project Manager | Jimmy/Josiah | 5 |  | 5 |  | 5 |  | 5 |  | 5
3
Iteration 5: | Development
|  | Add ability to export transactions to csv | Developer | Jimmy | 4 |  | 3 |  |  |  | 3 |  | 3
|  | Link buttons on home page to appropriate URLs | Developer | Jimmy | 2 |  | 1 |  |  |  | 1 |  | 1
|  | Fix issue where "Deposit" notifcations can't delete | Developer | Jacob | 2 |  | 2 |  |  |  |  | 2 | 2
|  | General stylistic improvments | Developer | Josiah/Jimmy/Jacob | 5 |  | 5 |  | 1.5 |  | 1.5 | 2 | 5
Analysis
|  | Quality Assurance/Testing New Systems | Tester/Project Manager | Jimmy/Josiah | 4 |  | 2 |  | 2 |  | 2 |  | 4
|  | Write Testing Manual | Developer | Josiah | 4 |  | 3 |  | 3 |  |  |  | 3
|  | Write User System Guide | Developer | Blake | 4 |  | 4 |  |  | 4 |  |  | 4
Total | [8 empty] | 81.5 | 83.5 | 92.25 | 74.75 | 301.5